## ProductBacklog
PRODUCT BACKLOG
SPRINT BACKLOG | US ID | BACKLOG ITEM |  |  | PRIORITY | RESPONSIBLE | ESTIMATE DATE | REMARKS
|  | AS A/AN | I WANT TO | SO THAT
1 | SB1/US1 | Developer | understand required technology | I can implement | 1 | HS+HA+MG | 2019-09-04
1 | SB1/US2 | Developer | configure machine | I can use that | 1 | HS+HA+MG | 2019-09-04
1 | SB1/US3 | Developer | create expression's image | It can be use for testing | 1 | HS+HA+MG | 2019-09-18
1 | SB1/US4 | Developer | extract text from image | It can be evaluated | 1 | HS+HA+MG | 2019-09-25
1 | SB1/US5 | Developer | test the result | result can be enhanced | 1 | HS+HA+MG | 2019-09-25
2 | SB2/US1 | Developer | Design UI | I get better results | 2 | HS+HA+MG | 2019-10-02
2 | SB2/US2 | Developer | deploy Flask | I will use funtions of it | 2 | HS+HA+MG | 2019-10-14
2 | SB2/US3 | Developer | apply AJAX | I can handel dataset | 2 | HS+HA+MG | 2019-10-14
2 | SB2/US4 | Developer | Design textbox | I can use dataframe | 2 | HS+HA+MG | 2019-10-25
2 | SB2/US5 | Developer | integration of all modules | I can clean the data | 2 | HS+HA+MG | 2019-10-25
3 | SB3/US1 | Developer | method to find out roots of an expression | prepared a list of it | 3 | HS+HA+MG | 2019-12-18
3 | SB3/US2 | Developer | method to find out roots of multiple expressions | I fill the missing values | 3 | HS+HA+MG | 2019-10-25
3 | SB3/US3 | Developer | method to find out diffrentiation | I applied suitable techniques | 3 | HS+HA+MG | 2019-10-25
3 | SB3/US4 | Developer | method to find out integration | I create graph | 3 | HS+HA+MG | 2020-01-02
3 | SB3/US5 | Developer | integration of all modules | I can visualize the noise | 3 | HS+HA+MG | 2020-01-02
4 | SB4/US1 | Developer | Prepare the environment for neural network | I dropped it | 4 | HS+HA+MG | 2020-01-09
4 | SB4/US2 | Developer | prepare and collect dataset | I did not get error | 4 | HS+HA+MG | 2020-01-09
4 | SB4/US3 | Developer | create model | dataframe will be sequenced | 4 | HS+HA+MG | 2020-01-16
4 | SB4/US4 | Developer | testing of the model | remove extra columns | 4 | HS+HA+MG | 2020-01-16
4 | SB4/US5 | Developer | Test the complete flask app | I can get some insights of data | 4 | HS+HA+MG | 2020-01-23

## SprintBacklog 1
SPRINT BACKLOG 1
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SB1/US1 | Understand the tools and technologies | SB1/US1/T1 | understand requirement of project | HS+HA+MG | Completed | 2019-09-04
|  | SB1/US1/T2 | choose appropriate language ot technologies | HS+HA+MG | Completed | 2019-09-04
|  | SB1/US1/T3 | search the desired modules and dataset | HS+HA+MG | Completed | 2019-09-04
|  | SB1/US1/T4 | search the required libraries used in Project | HS+HA+MG | Completed | 2019-09-04
SB1/US2 | configure machine | SB1/US2/T1 | install the required libraries for the selected language | HS+HA+MG | Completed | 2019-09-04
|  | SB1/US2/T2 | set the path for the complete project | HS+HA+MG | Completed | 2019-09-04
|  | SB1/US2/T3 | install the required libraries according to requirements | HS+HA+MG | Completed | 2019-09-04
|  | SB1/US2/T4 | run the sample code for testing the confriguation | HS+HA+MG | Completed | 2019-09-18
SB1/US3 | create expression's image | SB1/US3/T1 | create expression in MS-Paint | HS+HA+MG | Completed | 2019-09-18
|  | SB1/US3/T2 | store the image in png format | HS+HA+MG | Completed | 2019-09-18
|  | SB1/US3/T3 | store multiple type of expression | HS+HA+MG | Completed | 2019-09-18
|  | SB1/US3/T4 | store all the image at specific location | HS+HA+MG | Completed | 2019-09-18
SB1/US4 | extract text from image | SB1/US4/T1 | install the pytesseract | HS+HA+MG | Completed | 2019-09-18
|  | SB1/US4/T2 | apply pytesseract and filter to extract text from image | HS+HA+MG | Completed | 2019-09-25
|  | SB1/US4/T3 | store the text extracted from image | HS+HA+MG | Completed | 2019-09-25
SB1/US5 | test the result | SB1/US5/T1 | evaluate the extracted text using programming | HS+HA+MG | Completed | 2019-09-25
|  | SB1/US5/T2 | check the result is appropriate or not | HS+HA+MG | Completed | 2019-09-25
|  | SB1/US5/T3 | check the result on multiple expression | HS+HA+MG | Completed | 2019-09-25

## SB BD Ch01
Spring Backlog 01 burn down chart
Date | Planned Total Task | Actual Incomplete Task
2019-09-04 | 18 | 10 | Tasks
2019-09-18 | 10 | 5
2019-09-25 | 5 | 0
Days

## SprintBacklog 2
SPRINT BACKLOG 2
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SB2/US1 | Design UI | SB2/US1/T1 | Search the available UI design for proper fitting in our project | HS+HA+MG | Completed | 2019-10-02
|  | SB2/US1/T2 | Design UI with help of HTML, CSS & Bootstrap | HS+HA+MG | Completed | 2019-10-02
|  | SB2/US1/T3 | integrate into project | HS+HA+MG | Completed | 2019-10-02
|  | SB2/US1/T4 | test the UI | HS+HA+MG | Completed | 2019-10-02
SB2/US2 | deploy Flask | SB2/US2/T1 | create flask app | HS+HA+MG | Completed | 2019-10-02
|  | SB2/US2/T2 | apply the code in flask to fetch image | HS+HA+MG | Completed | 2019-10-02
|  | SB2/US2/T3 | apply the pytesseract code and solve expression | HS+HA+MG | Completed | 2019-10-02
|  | SB2/US2/T4 | send the result in json format to UI | HS+HA+MG | Completed | 2019-10-14
SB2/US3 | apply AJAX | SB2/US3/T1 | create AJAX code for sending & receiving the result | HS+HA+MG | Completed | 2019-10-14
|  | SB2/US3/T2 | create a block in UI to show selected image | HS+HA+MG | Completed | 2019-10-14
|  | SB2/US3/T3 | create a block in UI to show result | HS+HA+MG | Completed | 2019-10-14
|  | SB2/US3/T4 | apply AJAX code to get result on same interface/page | HS+HA+MG | Completed | 2019-10-14
SB2/US4 | Design textbox | SB2/US4/T1 | create textbox for the input of expression | HS+HA+MG | Completed | 2019-10-14
|  | SB2/US4/T2 | create a another block in UI to show result | HS+HA+MG | Completed | 2019-10-20
|  | SB2/US4/T3 | apply changes in Flask code to get result on same interface | HS+HA+MG | Completed | 2019-10-20
SB2/US5 | integration of all modules | SB2/US5/T1 | integrate all above models at one place | HS+HA+MG | Completed | 2019-10-20
|  | SB2/US5/T2 | check the result for input as image | HS+HA+MG | Completed | 2019-10-20
|  | SB2/US5/T3 | check the result for input through textbox | HS+HA+MG | Completed | 2019-10-20
|  | SB2/US5/T4 | test the complete modules after integration | HS+HA+MG | Completed | 2019-10-20

## SB BD Ch02
Spring Backlog 02 burn down chart
Date | Planned Total Task | Actual Uncompleted Task
2019-10-02 | 19 | 11 | Tasks
2019-10-14 | 11 | 6
2019-10-25 | 6 | 0
0
Days

## SprintBacklog 3
SPRINT BACKLOG 3
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SB3/US1 | method to find out roots of an expression | SB3/US1/T1 | find the ways to find out the roots of an equation | HS+HA+MG | Completed | 2019-12-18
|  | SB3/US1/T2 | select the best way to do it | HS+HA+MG | Completed | 2019-12-18
|  | SB3/US1/T3 | integrate into project | HS+HA+MG | Completed | 2019-12-18
|  | SB3/US1/T4 | test the project | HS+HA+MG | Completed | 2019-12-18
SB3/US2 | method to find out roots of multiple expressions | SB3/US2/T1 | find the ways to find out the roots of an equation | HS+HA+MG | Completed | 2019-12-18
|  | SB3/US2/T2 | select the best way to do it | HS+HA+MG | Completed | 2019-12-18
|  | SB3/US2/T3 | integrate into project | HS+HA+MG | Completed | 2019-12-18
|  | SB3/US2/T4 | test the project | HS+HA+MG | Completed | 2019-12-23
SB3/US3 | method to find out diffrentiation | SB3/US3/T1 | find the ways to find out the diffrentiation of an equation | HS+HA+MG | Completed | 2019-12-23
|  | SB3/US3/T2 | select the best way to do it | HS+HA+MG | Completed | 2019-12-23
|  | SB3/US3/T3 | integrate into project | HS+HA+MG | Completed | 2019-12-23
|  | SB3/US3/T4 | test the project | HS+HA+MG | Completed | 2019-12-23
SB3/US4 | method to find out integration | SB3/US4/T1 | find the ways to find out the integration of an equation | HS+HA+MG | Completed | 2019-12-23
|  | SB3/US4/T2 | select the best way to do it | HS+HA+MG | Completed | 2019-12-30
|  | SB3/US4/T3 | integrate into project | HS+HA+MG | Completed | 2019-12-30
SB3/US5 | integration of all modules | SB3/US5/T1 | add roots finder into project | HS+HA+MG | Completed | 2019-12-30
|  | SB3/US5/T2 | add diffrentiation finder into project | HS+HA+MG | Completed | 2019-12-30
|  | SB3/US5/T3 | add integration finder into project | HS+HA+MG | Completed | 2019-12-30
|  | SB3/US5/T4 | check the project | HS+HA+MG | Completed | 2019-12-30

## SB BD Ch03
Spring backlog 3 Burnt Down chart
Date | Planned Total Task | Actual Uncompleted Task
2019-12-18 | 19 | 12 | `
2019-12-23 | 12 | 7
2019-12-30 | 7 | 0
0
Days

## SprintBacklog 4
SPRINT BACKLOG 4
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SB4/US1 | Prepare the environment for neural network | SB4/US1/T1 | import keras | HS+HA+MG | Completed | 2020-01-09
|  | SB4/US1/T2 | import pandas | HS+HA+MG | Completed | 2020-01-09
|  | SB4/US1/T3 | set required parameters | HS+HA+MG | Completed | 2020-01-09
|  | SB4/US1/T4 | check the installation | HS+HA+MG | Completed | 2020-01-09
SB4/US2 | prepare and collect dataset | SB4/US2/T1 | collect hand written numbers dataset | HS+HA+MG | Completed | 2020-01-09
|  | SB4/US2/T2 | prepare dataset for the required ones | HS+HA+MG | Completed | 2020-01-09
|  | SB4/US2/T3 | Remove noise from the data set | HS+HA+MG | Completed | 2020-01-09
|  | SB4/US2/T4 | merge dataset in standard form | HS+HA+MG | Completed | 2020-01-09
SB4/US3 | create model | SB4/US3/T1 | search the available models for the data set | HS+HA+MG | Completed | 2020-01-16
|  | SB4/US3/T2 | train dataset from different model | HS+HA+MG | Completed | 2020-01-16
|  | SB4/US3/T3 | find out the scores of all models | HS+HA+MG | Completed | 2020-01-16
|  | SB4/US3/T4 | find out the best model | HS+HA+MG | Completed | 2020-01-16
SB4/US4 | testing of the model | SB4/US4/T1 | test the model with the dataset present | HS+HA+MG | Completed | 2020-01-16
|  | SB4/US4/T2 | test the model with the appropriate input | HS+HA+MG | Completed | 2020-01-23
|  | SB4/US4/T3 | create the pickle file | HS+HA+MG | Completed | 2020-01-23
SB4/US5 | Test the complete flask app | SB4/US5/T1 | Deploy the flask app | HS+HA+MG | Completed | 2020-01-23
|  | SB4/US5/T2 | Give input in image format to check the result | HS+HA+MG | Completed | 2020-01-23
|  | SB4/US5/T3 | Give input in text format to check the result | HS+HA+MG | Completed | 2020-01-23
|  | SB4/US5/T4 | check the results of both image and text | HS+HA+MG | Completed | 2020-01-23

## SB BD Ch04
Date | Planned Total Task | Actual Uncompleted Task
2020-01-09 | 19 | 11 | Tasks
2020-01-16 | 11 | 6
2020-01-23 | 6 | 0
0
Days